## Gantt
Week beginning:		7 Jul	14 Jul	21 Jul	28 Jul	4 Aug	11 Aug	18 Aug	EMF
Structural
Pole Insertion
Buy cable ties & h/w
Control Tent
Buy poles
Build Poles
Build jig
Electrical
Buy Cable
Buy PSUs
Implementation
Mains connection
Electronic
Design
Buy LEDs
Other Procurement
Implementation
Control s/w
Lighting Control s/w
Android app
CV
Design
Implementation
Testing
Integration
Lighting Testing
Integration Testing

Block colours indicate confidence of timeliness, green being most confident, red least