## Gantt
		7-13 Jul	14-20 Jul	21-27 Jul	28-3 Aug	4-10 Aug	11-17 Aug	18-24 Aug	EMF
Structural
Pole Insertion
Buy cable ties & h/w
Control Tent
Buy poles
Build Poles
Build jig
Electrical
Buy Cable
Buy PSUs
Implementation
Mains connection
Electronic
Design
Buy LEDs
Other Procurement
Implementation
Control s/w
Lighting Control s/w
Android app
CV
Design
Implementation
Testing
Integration
Lighting Testing
Integration Testing

Block colours indicate confidence of timeliness, green being most confident, red least